## OLD NATA Corridors & Projects
# | Corridor/ Operation | Project | Limits | Scope | Type of Project | Cost Estimate | 2017-2018 Strategies | Funding Already Identified | Types of Funding Opportunities | DRCOG 2035 FC-RTP | 2017 Project Update | New in 2017/tier | 2014 Tier | Criteria | Comments/Notes
Tier I Projects -- regionally significant projects NATA taking lead to actively support
1 | I-25 | North I-25 Preferred Package from PEL Study | US 36 to SH 7 | As identified in the PEL. Includes general purpose lanes, bus operational improvements, traffic operations improvements, bridge reconstruction at 88th Avenue, extension of express lanes between E-470 and SH 7, auxiliary lanes between interchanges, cross-section that includes inside and outside shoulders. | Capacity, traffic operations, enhanced transit services |  | Focus on critical improvements needed by 2025 identified in I-25 PEL. Pursue partnerships with CDOT, FHWA, DRCOG to leverage available RAMP, TIGER, TIFIA, other funding. -- May/June time frame Work with CDOT to reconcile 2040 RTP to make sure capacity improvements are included -- May/June timeframe Work with State Legislature/HPTE and CDOT on P3 legislation. Bundle improvements with extention of express toll lanes project to S.H. 7 |  | I-25 Metro District DRCOG RTD Toll Revenues CDOT RAMP TIGER P3 RAMP TIFIA | 2011 Cycle Amendment: The south segment includes interim HOV/HOT lanes extending from US-36 to 120th Avenue to be implemented in the 2015-2024 staging period. An additional $159 million is allocated through 2035 for the TELs and other general purpose, safety and operational improvements as identified in the I-25 PEL Study, scheduled to begin in 2011. Work with CDOT to reconcile 2040 RTP to make sure capacity improvements are included -- May/June timeframe | EA underway, 30 percent design underway for general purpose lanes between US 36 and Thornton Parkway, 88th Avenue Bridge reconstruction, 88th Avenue RTD median station, and auxiliary lanes between interchanges.
2 |  | I-25 Managed Lanes | Between 120th Avenue and E-470 | Extend Managed Lanes | Capacity, traffic operations, enhanced transit services, and ridesharing opportunities | [5 empty] | Construction underway between 120th Avenue to E-470 for managed lanes and auxiliary lanes between 136th Avenue and 144th Avenue.
3 |  | I-25 Managed Lanes | Between E-470 and SH 7 | Extend Managed Lanes | Capacity, traffic operations, enhanced transit services, and ridesharing opportunities | [5 empty] | Final design should be completed by late 2017/early 2018.
4 |  | I-25 and SH 7 Interchange |  | Reconstruct interchange as a multimodal hub, diverging diamond interchange | Capacity, traffic operations, enhanced transit services, enhanced bicycle and pedestrian movements, and ridesharing opportunities | [5 empty] | EA underway. Design underway with anticipated 30 percent plans late 2017 or early 2018
5 |  | I-25 Express Lanes conversion to bi-directional | Downtown Denver to US 36 | Study and provide interim Bus on Shoulder (BUS) on I-25 | Capacity and Bus/managed lane operational improvements | [5 empty] | Study underway should be complete late 2017.
6 |  | I-25 and SH 7 Interchange |  | Reconstruct interchange as a multimodal hub, diverging diamond interchange | Capacity, traffic operations, enhanced transit services, enhanced bicycle and pedestrian movements, and ridesharing opportunities | [5 empty] | EA underway. Design underway with anticipated 30 percent plans late 2017 or early 2018
7 |  | I-25 HOT Lanes Conversion to bi-directional | DT Denver to U.S. 36 | Build interim (shoulder running) lanes. | Capacity & bus/managed lane Operational Improvements | $600k for interim peak hour shoulder running $5-$20 million for additional capacity improvements | Work with DRCOG, CDOT and FHWA for any needed inclusion of interim project into DRCOG Fiscally constrained plan. Work with RTD/CDOT on prioritizing |  | RTD Local CDOT Excess U.S. 36/existing I-25 managed lanes excess toll revenues TIFIA TIGER
8 | I-25 Regional Bus Service |  | Longmont/S.H. 119 to Downtown Denver via I-25 with stops at 119, S.H. 7 and new 88th median station. Both 88th median station and new bus service from S.H. 7 to 120th identified in I-25 PEL |  | Regional Bus service |  | Work with CDOT Rail & Transit Division, RTD and local jurisdictions on elements that need to be in place for regional service (I.e., park & rides at 119, S.H. 7 and 88th Ave.) Consider DRCOG application for transit funding in next round of the TIP: |  | FASTER Transit RTD DRCOG
9 | I-270 | I-270 Corridor Improvements | Full extent | Add managed lanes, improve Vasquez blvd, general purpose capacity improvements | Capacity and operational improvements | Adding 1 lane each direction -$270m EA $3 m | Consider TIGER grant application. Continue ongoing discussions with CDOT, HPTE and Denver, as needed in connection to I-70 EIS. Potential future use of the corridor to reroute traffic during construction on I-70. Support continued inclusion in FC-RTP. Begin NEPA & preliminary design (30%) for corridor. | I-70 EIS | P3 CDOT HPTE | Add two GP lanes ($49.3 million)
10 | North Metro | FasTracks | Phase II - 124th/Eastlake to 162nd Avenue | Complete FasTrack "N" line as approved by the voters | Transit | [5 empty] | RTD projecting it will be past 2040 before being completed
11 | Northwest Rail |  | Phase II | extend rail line from Westminster Station to next reasonable phase | Transit | TBD | Provide input into recommendations from the NAMS study to RTD | RTD RAM | SmallStarts TIGER TIFIA DRCOG | TBD
11 | 120th Avenue | S.H. 128 | Pecos to Zuni | Key intersection improvements need to enhance overall safety of corridor. Dedicated right turn lanes at Zuni (EB and WB), Tejon (EB) and Pecos (WB). Adequate ROW for new turn lanes already exist | operational improvements | TBD | NATA activiely supports project submittal |  | STP-Metro CDOT RPP |  |  | 2
12 |  | Arterial BRT Improvements | Broomfield P&R to AdCo Govt Ctre | Stops per NAMS and NATE studies | Transit | 18971996 | Support as recommended near term service in NAMS study. Refine cost estimates and service in NATE |  |  |  |  | 2
13 | S.H. 7 | Arterial BRT Improvements | Brighton to Boulder | Regional Bus Rapid Transit route planning | Transit |  |  | DRCOG, RTD | Small Starts, DRCOG CMAQ |  | Study indicates BRT is feasible. Starting Phase II study for specifics on station location/design standards and consistency/access
Tier II Projects -- actively pursuing support/monitoring (Tier II includes studies and projects with smaller areas of influence, and NATA members take lead)
14 | I-76 | New Interchange | I-76 & Bridge St. | Add ramps to current overpass | Operational Improvements | 10000000 | Support Brighton's request to include FC- RTP Encourage NEPA to start in Sept. |  |  | Include in 2035 FC-RTP for $20 million
15 | North Metro Extension | ICS and Commuter Rail | Between RTD "N" Line and Longmont | High Speed Rail (ICS) north to Fort Collins and south to Colorado Springs. Commuter Rail between RTD and Longmont including station(s) for Tri-towns. | Transit | [5 empty] | CDOT has completed both a commuter rail and ICS study. The commuter rail was proposed on the 10-year plan. The ICS study was updated in 2017 to include two additional alternates - all three alternates use the station at 162nd and Colorado (end of line for the "N" line)
16 | U.S. 287 | Arterial BRT Improvements | Longmont to Broomfield P&R to downtown Denver | Main Street & S.H. 66 to Broomfield P&R @ Uptown Ave/Wadsworth (local jurisdictions desire service to continue down U.S. 36 into Downtown Denver) | Transit | 39758740 | Support in NAMS study recommendation Work with RTD and other jurisdictions to identify funding | RTD RAM | RAMP FASTER Transit SmallStarts NewStarts (corridor-based) RTD DRCOG |  | Pending NAMS TAC meeting scheduled for Provide letter of support that Sharon Richardson can present at the April 18th PAC meeting in support of Arterial BRT along this corridor.
17 | 104th Avenue (SH 44) | 104th Avenue (SH 44) widening | Between Grandview Ponds and US 85 | Widen 104th Avenue (SH 44) to a 4-lane principal arterial. Includes trail/sidewalk(s). | Capacity, Bicylce and Pedestrian |  |  |  |  | Included in 2040 FC RTP: $48.7 Million | Bridge over the South Platte River has been widened to 4 lanes with trail/sidewalks. State has approached jurisdictions about devolution.
18 | S.H. 52 | Widening through Dacono and Frederick | City limits of Dacono and Frederick | Widening roadway with interseciton improvements at WCRs -- 3, 5, & 7. | Road Capacity | TBD | Consider conducting study for ACP |  | Union Pacific STP-Metro Local Funds |  | We have been awarded HSIP funding for adding an acceleration lane for the northbound I-25 to eastbound SH 52 traffic. This was a joint application by Dacono and Frederick and will be administered by Frederick. The RFP to select a design firm should go out within the next month.
19 | U.S. 85 | PEL: New Interchange | U.S. 85 & 120th |  | Operational Improvements | 25000000 | Support the refinement of EA in PEL study; discuss other interhcange configurations, etc.
20 |  | PEL: Transit Operational Improvements | Pavillions, south of S.H. 7 on NB side | Add NB bus slip ramp for RTD bus operations | Operational Improvements | TBD | Visit configuration of slip ramps in PEL study
21 |  |  | 60th & U.S. 85 | Intersection improvments (future interchange) | Operational Improvements | 1500000 | Support CDOT-sponsored study Work with Denver and CDOT to incorporate into local plans and I-70 EIS respectively |  | CDOT Local
Tier III Projects -- Projects in queue (horizon projects)
22 | S.H 119 | Queue Jumps and Aux Lanes | Sunset St to Bowen St | Install bus queue jumps and auxillary lanes | Operational Improvements
23 | Sheridan Blvd. | S.H. 95 Capacity Improvements | 87th to 91st | Widen and replacement of bridge over BNSF. |  |  |  |  | TBD |  |  | 4
New Projects -- To Be Tiered
24 | Sheridan Boulevard | US 36 Bikeway grade separations at Sheridan Boulevard and Church Ranch Boulevard. Sheridan Boulevard from five thru lanes to six. Multi-modal Improvements (SH 95) | US 36 Bikeway and Sheridan BRT Station and Church Ranch BRT Station. Roadway Widening from US 36 Bridge to 88th Avenue. | Construct remaining grade separatoins of US 36 Bikeway at Sheridan Boulevard and Church Ranch Boulevard.Widening of Sheridan is included on the DRCOG TIP wait list from 2014. This project also includes partial reconstruction of the RTD Park n Ride at Sheridan Blvd. to incorporate a grade separation to facilitate future autonomous transit vehicles, bikes and pedestrians. | Capacity, Transit, Bicycle and Pedestrian |  | Complete 30% Design for cost estimate. Submit TIGER grant. | Westminster to provide local match. CDOT will pledge some match for TIGER grant. | Federal, DRCOG with local match | Included in 2040 FC RTP | 30% Design of the Sheridan grade separation is funded by Westminster. This project will be submitted as a TIGER grant to fully fund designa nd construction. If it does not receive federal funding, TIP funding will be sought. | 2 | TIER 2 |  | Should this be included in the Sheridan project?
25 | 120th Avenue | Key intersection improvements for safety and transit enhancement. | Zuni and Pecos | Evalulate dedicated right turn lanes and que jumps for transit. | Operational and Transit |  |  |  | STP Metro, Local |  |  | 2 | TIER II |  | group w/ 120th corridor
26 |  | 120th Avenue Widening | Washington Street to York | Widening to 6-lane cross-section, with right turn lanes, double turn lanes at key intersections, traffic signal modifications, one new traffic signal and 10' wide multi-use trail where possible. | Capacity, transit, bicycle and pedestrian | Will provide update | Completed corridor study and cost estimate in 2015. | FC RTP as appropriate | DRCOG |  | Not currently on projects list, but 120th included on Regional Roadway Map | 2 | PEL |  | Will follow-up if BRT needs to be involved. If not added to, design so it can be added in future.
27 |  | Widening US-85 to E-470 | Initial project would widen from Chambers Road to E-470 (1.35 miles) | The project will widen 1.35 miles of roadway from 2 lanes (one in each direction) to 4 lanes (two in each directon) with on-street bike lanes and an adjacent sidewalk & multi-use trail. Interconnection of the traffic signals will occur in order to improve corridor efficiency and levels of service. New signals will be installed, as warranted. | Capacity, traffic operations, bicycle and pedestrian improvements | $15.5M | Determine project scope; identify parternships & funding from local developers |  | DRCOG Developer |  |  | 2 |  |  | 120th corridor
28 | Thornton Parkway | Thornton Parkway / 96th Avenue over the South Platte River | Between I-76 and Riverdale Road | Widening and Extension of Thornton Parkway over the South Platte River | Capacity, Transit, Bicycle and Pedestrian |  | Adopt an IGA to preserve ROW, Start PEL process, update DRCOG FC-RTP as appropriate |  | Developer |  | IGA being considered to preserve ROW as development occurs | 4
29 | Rail | Extend B Line (Northwest) from Westminster Station to next reasonable phase | Downtown Westminster Station is located at 88th and Harlan | Build three miles of track and station at Downtown Westminster or extend rail line from Westminster Station to next reasonable phase | Transit |  | Work with RTD to determine feasibility. |  |  |  | Westminster is researching the cost to extend the line to Downtown Westminster and partnering with jurisdictions along the full B Line alignment to Longmont to explore peak rail service with operation of a few peak hour trains. | 1 | TIER II | all
30 |  | North Metro (N Line) First / Last Mile Connections | At stations, 72nd Avenue to 124th Avenue | Provide first / last mile connections to stations | Transit, bicycle, and Pedestrian |  | Work with RTD to have service provided by Fix Route and Call-n-Ride. Continue to complete street, trail, sidewalk projects. Look at alternative transit services. | RTD, DRCOG | Developer, DRCOG, RTD, local |  | Trails, sidewalks and bicycle lanes being installed. RTD is starting to look at bus routing changes | 2
31 | Bike Share | Bike share in multiple jurisdictions, sub-regional impact | At stations, 72nd Avenue to 124th Avenue | Implementation of Bike Share program | Bicycle |  | Work with Smart Commute on possible master contract. Continue to explore if feasible. Develop agreement to have Smart Commute run the program. | Private | Private |  | Exploring possible locations | 2
32 | Undefined areas | Provide bus service in transit drought islands and areas | Areas not currently served | Transit service study of bus service to major employment and residential areas that meet RTD service area quidelines | Transit |  | Work with RTD to have service. |  |  |  |  | 4
33 | 72nd Avenue | Conduct a study to determine safety and mobility improvements for 72nd Avenue | 72nd Ave between Sheridan and Lowell Blvds. | Study to assess the repurposing of 72nd Avenue to included widening the sidewalks, enhancing transit stops and bicycle facility connections. | Pedestrian and transit | $150K |  |  | DRCOG STAMP Grant |  | Concept Study | 3 | Tier III
34 | Federal Boulevard | Conduct a study to determine needs for multi-modal infrastructure. | US 36 to W. 84th Avenue | Study to establish a transportation vision for Federal Boulevard that addresses pedestrain safety issues and recommendes multi-modal transportation infrastructure. | Transit and pedestrian | $200K |  |  | DRCOG STAMP Grant |  | Concept Study | 3 | Tier III
35 | State highways (i.e. SH 7, 287, 120th) | Regional signal optimization and safety project | need more info from Gary (Erie) | [11 empty] | Follow-up
36 | 88th Avenue | Widening from 2 lanes to 4 lanes with bike lanes, trails & sidewalks | I-76 to Highway 2 | 88th Avenue is a regional roadway serving as a connection between a freeway and a major regional arterial. The project will widen 1.6 miles of roadway from 2 lanes (one in each direction) to 4 lanes (two in each directon) and on-street bike lanes with an adjacent sidewalk & multi-use trail. Interconnection of the traffic signals will occur in order to improve corridor efficiency and levels of service. | capacity, traffic operations, pedestrian & bicycle | $26.2M | A design firm will be selected in late-2017/early-2018 to complete the preliminary design and NEPA clearance. Goal is to complete this work by the end of 2018. | $300K included in DRCOG RTP for NEPA and preliminary design | DRCOG | NEPA & Preliminary design included in 2035 FC-RTP | Consultant selection process is underway. | 3
37 | West 144th Avenue/ Dillon Road | Dillon Rd/ West 144th Ave Improvements | Northwest Parkway to Zuni | Dillon Rd/W 144th is a regional roadway with connectivity to US287 and I-25. The project will widen the 4-mile Dillon Road/West 144th Avenue corridor through Broomfield to four continuous through lanes from US 287 to Zuni Street. The roadway will be designed in general conformance with the master plan and will include pedestrian/bicycle access improvements. | capacity, traffic operations, pedestrian & bicycle | $40.2 M |  |  |  | YES - local project |  | 2
38 |  | Sheridan & 144th Ped/Bike Crossing | Sheridan Blvd at W 144th | Pedestrian and bicycle grade separated crossing. Crossing is on a major regional trail. The Broomfield Trail provides a connection from southwest Broomfield to the northeast, east of I-25. The trail crosses the US 287 and SH 7 corridors as well. Upon completion will be 22.5 mile trail. | pedestrian & bicycle, supports multimodal | Vision Project | [5 empty] | 4 |  |  | first needs study
39 | 160th Ave. | 160th Ave. Improvements | Sheridan to I-25 | Add lanes 3 & 4 | Capacity, traffic operations, pedestrian/ bicycle | $3.8 M |  |  |  | YES - local project |  | 2
40 |  | 160th Avenue Overpass | 160th Ave at I-25 | Expand capacity at 160th overpass | Capacity, traffic operations, pedestrian/ bicycle | Vision Project | [5 empty] | not discussed in meeting
41 | Sheridan Parkway | Sheridan - Lowell to NW Parkway | Lowell to NW Parkway | Developers will widen road to 4 lanes, ultimate requires a 6 lane expansion. | capacity, operational improvments, ped/bicycle improvements | $7.6 M |  |  |  | YES - local project |  | 4
42 |  | Sheridan - NW Parkway to SH7 | NW Parkway to SH7 | Add lanes 3 & 4 | capacity, operational improvments, ped/bicycle improvements | $5.7 M |  |  |  | YES - local project |  | 4 |  |  | potentially combined with Sheridan & I-25 interchange project?
43 |  | Sheridan - SH7 to Weld County Road 11 | SH7 to Weld County Road 11 | Expand and extend Sheridan Road from SH7 to Weld County Road 11, crossing I-25 | capacity, operational improvments, ped/bicycle improvements | Vision Project | [5 empty] | 4
43 | I-25 | Sheridan & I-25 interchange | Sheridan Parkway at I-25 | New interstate interchange at the new Sheridan road expansion, project will include grade separated pedestrian and bicycle facilities | capacity, operational improvments, ped/bicycle improvements | Vision Project | [5 empty] | 4 |  |  | potentially combined with Sheridan Blvd., SH7 to I-25 project
44 |  | Regional pedestrian and bike path similar to 36 | need more info from Gary (Erie) | [8 empty] | 4 |  |  | Bundle under I-25 corridor. First needs feasibility study and more clarification
45 |  | Broomfield Trail & Bull Canal Grade Separated Crossing | Broomfield Trail at I-25 | Pedestrian and bicycle grade separated crossingg on Broomfield Trail & Bull Canal at I-25. Crossing is on a major regional trail. The Broomfield Trail provides a connection from southwest Broomfield to the northeast, east of I-25. The trail crosses the US 287 and SH 7 corridors as well. Upon completion will be 22.5 mile trail. | pedestrian, bicycle, multi-modal | [6 empty] | 4
46 | SH 7 | Implementation of PEL's | Brighton to US 287 (NEW) | Widen Road, install bike lanes, trails, sidewalks, implement BRT, implement PEL | Capacity, Transit, Bicycle and Pedestrian |  | Continue to have work done with development. Work with CDOT to put on 10-year plan. |  | FASTER Transit, SB17-267, Developer, STP |  | Portions are being widened by development. Other areas will require government funding. | 2
47 |  | SH7 Improvements | Boulder County LIne to Sheridan Parkway | widen from 2 to 4 lanes, multimodal improvements | capacity, operations, multimodal, bus rapid transit | $6.6M |  |  |  | YES - local project |  | 2
48 |  | SH 7 Improvements | Sheridan Parkway to I-25 | Widen from 2 to 4 lanes, multimodal improvements | capacity, operations, multimodal, bus rapid transit | $10.2 M |  |  |  | YES - local project |  | 2
49 |  | SH7 at Huron Grade separated crossing | SH7 at Huron | Pedestrian and bicycle grade separated crossing. Crossing is on a major regional trail. The Broomfield Trail provides a connection from the Great Western Reservior Open Space in southwest Broomfield to the northeast, east of I-25. The trail crosses the US 287 and SH 7 corridors as well. Upon completion will be 22.5 mile trail. | pedestrian, bicycle, multi-modal, support BRT | [6 empty] | 2
50 | Huron Street | Huron Street Improvements | 150th to 160th Ave | Add lanes 3 & 4 | Capacity, traffic operations, pedestrian/ bicycle, multimodal potential BRT connection at SH7 micro mobility hub | $8.6 M |  |  |  | YES - local project |  | not discussed in meeting
51 |  | Huron Street Improvements | 160th Ave. to SH 7 | Relocate and add lanes 3 &4 | Capacity, traffic operations, pedestrian/ bicycle, multimodal potential BRT connection at SH7 micro mobility hub | $5.1 M |  |  |  | YES - local project |  | not discussed in meeting
52 | Northwest Parkway | Northwest Parkway Trail Underpass Retrofit | Northwest Parkway Trail west of Wildgrass | Retrofit a substandard underpass. Project will connect from trails in Wildgrass to Rock Creek Trail and Coal Creek Trail, upon completion of the trail Broomfield and Louisville and the I-25 corridor will be connected. | pedestrian, bicycle, supports multimodal | Vision Project | [5 empty] | 3 |  |  | Is this a DRCOG project b//c it's goingt to be interconnected?
awaiting approval since outside of NATA boundaries | US 287 | US 287 to US 36, Hoyt Street Pedestrian & Bicycle Overpass | Midway Blvd to Industrial Lane | Build an overpass over BNSF RR and Industrial Lane at Hoyt Street. Grade separated crossing connects the underpass to US 36 Bikeway. Project is critical to connecting US 287 via Midway Blvd to US 36 Bikeway | pedestrian & bicycle, supports multimodal | $3.1M | [5 empty] | 2 |  |  | wait for determination if this gets removed from list because it goes west of 287 (outside of NATA boundaries; DRCOG project) and doesn't meet all criteria

## Revised NATAProjects 6-25-20
Project # | Corridor/ Operation | Project | Limits | Jurisditions | Scope | Type of Project | Cost Estimate | 2020-2023 Strategies | Funding Already Identified | Types of Funding Opportunities | DRCOG 2040 FC-RTP | 2020 Project Update | New in 2017/tier | 2014 Tier | Criteria | Comments/Notes
Priority Projects -- regionally significant projects NATA taking lead to actively support
1 | I-25 | North I-25 Preferred Package from PEL Study | US 36 to CO 7 |  | As identified in the PEL. Includes general purpose lanes, bus operational improvements, traffic operations improvements, bridge reconstruction at 88th Avenue, extension of express lanes between E-470 and CO 7, auxiliary lanes between interchanges, cross-section that includes inside and outside shoulders. | Capacity, traffic operations, enhanced transit services |  | Focus on critical improvements needed by 2025 identified in I-25 PEL. Pursue partnerships with CDOT, FHWA, DRCOG to leverage sources of other available funding. Work with CDOT to reconcile 2040 RTP to make sure capacity improvements are included -- May/June timeframe Work with State Legislature/HPTE and CDOT on P3 legislation. Bundle improvements with extension of express toll lanes project to CO 7 |  | DRCOG RTD Toll Revenues Federal Grants TIFIA | 2011 Cycle Amendment: The south segment includes interim HOV/HOT lanes extending from US-36 to 120th Avenue to be implemented in the 2015-2024 staging period. An additional $159 million is allocated through 2035 for the TELs and other general purpose, safety and operational improvements as identified in the I-25 PEL Study, scheduled to begin in 2011. Work with CDOT to reconcile 2040 RTP to make sure capacity improvements are included -- May/June timeframe | EA underway, 30 percent design underway for general purpose lanes between US 36 and Thornton Parkway, 88th Avenue Bridge reconstruction, 88th Avenue RTD median station, and auxiliary lanes between interchanges.
2
3 |  | I-25 Managed Lanes | Between E-470 and CO 7 | Thornton, Erie, Broomfield, Adams County | Extend Managed Lanes | Capacity, traffic operations, enhanced transit services, and ridesharing opportunities | [5 empty] | Final design should be completed by late 2017/early 2018.
4 |  | I-25 and CO 7 Interchange | I-25 and CO 7 Interchange | Thornton, Broomfield, Adams County | Reconstruct interchange as a multimodal hub, diverging diamond interchange | Capacity, traffic operations, enhanced transit services, enhanced bicycle and pedestrian movements, and ridesharing opportunities | $200m to construct both I-25 Segment 3B and the Mobility Hub interchange | Work with CDOT to identify next stategic steps to implement next reasonable phase to allow transit access | $10m in the CDOT 10 year vision plan | BUILD, other federal grants, DRCOG TIP |  | EA underway.10% to 15% design concept/plans complete.
5 |  | I-25 Express Lanes conversion to bi-directional | Downtown Denver to US 36 | Denver, Adams County | Ultimately construct bi-directional Express Lanes | Capacity and Bus/managed lane operational improvements | NAMS Estimate: $600k for interim peak hour shoulder running NAMS Estimate: $5-$20 million for additional capacity improvements | Work with DRCOG, CDOT and FHWA for any needed inclusion of interim project into DRCOG Fiscally constrained plan. Work with RTD/CDOT on prioritizing |  | RTD Local CDOT Excess US 36/existing I-25 managed lanes excess toll revenues TIFIA TIGER |  | Study completed late 2017. CDOT does not find BOS to be cost effectives at this time. Revisit when Central I-25 PEL is complete. HPTE completed a study of managed lanes in CO. This segment was listed on the higher priority list
6 | I-25 Regional Bus Service | I-25 Regional Bus Service | Longmont/CO 119 to Downtown Denver via I-25 with stops at CO 119, CO 7 and new 88th median station. Both 88th median station and new bus service from CO 7 to 120th identified in I-25 PEL | Longmont, Erie, Tri-towns (Frederick, Firestone, Dacono), Thornton, Westminster, Northglenn, Denver, Broomfield, Adams County, Weld County, | Longmont/CO 119 to Downtown Denver via I-25 with stops at CO 119, CO 7 and new 88th median station. Both 88th median station and new bus service from CO 7 to 120th identified in I-25 PEL Should this be 84th? | Regional Bus service |  | Work with CDOT Rail & Transit Division, RTD and local jurisdictions on elements that need to be in place for regional service (I.e., park & rides at CO 119, CO 7 and 88th Ave.) |  | FASTER Transit RTD DRCOG |  | update??
7 | I-270 | I-270 Corridor Improvements | Full extent | Adams County, Commerce City, Denver | Add managed lanes, improve Vasquez Blvd, general purpose capacity improvements | Capacity and operational improvements | Adding 1 lane each direction -$270m EA $3 m | Consider TIGER grant application. Continue ongoing discussions with CDOT, HPTE and Denver, as needed in connection to I-70 EIS. Potential future use of the corridor to reroute traffic during construction on I-70. Support continued inclusion in FC-RTP. Begin NEPA & preliminary design (30%) for corridor. | I-70 EIS | P3 CDOT HPTE | Add two GP lanes ($49.3 million) | Didn't significant work get funded through the last TIP?
8 |  |  | 60th & U.S. 85 | Commerce City | Intersection improvements | Operational/Safety Improvements | TBD through Vasquez Preliminary Cost Estimate is approximately $22M | Work with CDOT through Vasquez PEL | $4.75 M (DRCOG) $1.5M (Commerce City) $5.75M (CDOT) | CDOT Local BUILD Grant
9 | North Metro | FasTracks | Phase II - 124th/Eastlake to 162nd Avenue | Eastlake, Thornton | Complete FasTrack "N" line as approved by the voters | Transit | [5 empty] | RTD projecting it will be past 2040 before being completed
| 104th Avenue (SH 44) | 104th Avenue (SH 44) widening | BetweenColorado Boulevard and US 85 | Thornton, Commerce City | Widen 104th Avenue (SH 44) to a 4-lane principal arterial. Includes trail/sidewalk(s). | Capacity, Bicycle and Pedestrian |  | DRCOG TIP project approved for preliminary and environmental plans. | DRCOG, Local Governments | Federal, DRCOG, local match | Included in 2040 FC RTP: $48.7 Million | Bridge over the South Platte River has been widened to 4 lanes with trail/sidewalks. State has approached jurisdictions about devolution.
10 | 120th Avenue | CO 128 | Pecos to Zuni | Westminster | Key intersection improvements need to enhance overall safety of corridor. Dedicated right turn lanes at Zuni (EB and WB), Tejon (EB) and Pecos (WB). Adequate ROW for new turn lanes already exist | operational improvements | TBD | NATA actively supports project submittal |  | STP-Metro CDOT RPP |  | The intersections of SH 128 should stay in Endorsed category. | 2
11 |  | Arterial BRT Improvements | Broomfield P&R to AdCo Govt Ctre | Broomfield, Westminster, Northglenn, Thornton, Commerce City, Brighton, Adams County | Stops per NAMS and NATE studies | Transit | 18971996 | Support as recommended near term service in NAMS study. Refine cost estimates and service in NATE Implement Broomfield US 287/120th Ave. Multimodal & Safety Study | 2021-2022 $600,000 TIP for Multimodal & Safety Study along US 287/120th Ave. in Broomfield. Lead by CDOT |  |  | Segment from Federal Blvd to Wagon Rd. also serves the terminus for the Federal Blvd. BRT as identified in the RTD BRT Study. Broomfeild secured TIP funding for Multimodal Study along Broomfield Segment. | 2
12 | CO 7 | Arterial BRT Improvements | Brighton to Boulder | Brighton, Thornton, Broomfield, Erie, Lafayette, Boulder | Regional Bus Rapid Transit route planning, preliminary engineering and design, and widening, Pedestrian shared use path and Bicycle lanes | Transit, roadway | $200M for both I-25 Segment 3B and the Interchange) | Work with CDOT to identify next stategic steps to implement next reasonable phase to allow transit access | DRCOG, RTD | Small Starts, DRCOG CMAQ, federal grants |  | Study indicates BRT is feasible. Phase II study for specifics on station location/design standards and consistency/access is complete. Starting Preliminary and Environmental Engineering.
13 | CO 52 | Intersection Improvements | City limits of Dacono and Frederick | Dacono, Frederick | Additional Scope Intersection improvements: WRC11 (York St); Glen Creighton Dr.; WCR15 (Holly St); S-curve @ WRC17; WRC19 | Road Capacity, Safety (Glen Creighton Dr) | TBD | Consider conducting study for ACP |  | Union Pacific STP-Metro Local Funds |  | We have been awarded HSIP funding for adding an acceleration lane for the northbound I-25 to eastbound CO 52 traffic. This was a joint application by Dacono and Frederick and will be administered by Frederick. The RFP to select a design firm should go out within the next month. // 2020 - Active community led PEL & ACP ongoing.
14 | U.S. 85 | PEL: New Interchange | U.S. 85 & 120th | Commerce City |  | Operational Improvements | 25000000 New Cost Estimate = $90M | Support the refinement of EA in PEL study; discuss other interchange configurations, etc. | Preconstruction Activites/ROW DRCOG FY21 = $4.2M DRCOG FY22 = $2.1M Local Match = $5.3M CDOT = $1M Total = $12.6 M | CRISI Grant
15 | Sheridan Boulevard | Widen Sheridan from US 36 to 88th Ave, build grade separation of US 36 Bikeway for pedestrians, bikes and autonomous vehicles. | Roadway widening; US 36 Bridge to 88th. | Westminster | Widen Sheridan Boulevard, construct underpass of US 36 Bikeway near Sheridan BRT Station for pedestrians, bikes and autonomous vehicles. Includes partial reconstruction of US/Sheridan Park n Ride | Capacity, transit, bicycle, pedestrian | $8M | TIGER Grant submitted |  | Federal, DRCOG, local match | Included in 2040 FC RTP | Westminster is preparing 30% Design for bikeway underpass. Final design underway - construction 2021/22 | 2 | TIER 2
| Federal Boulevard | safety and multimodal improvements to create a community serving boulevard. | 120th to 52nd | Westminster, Federal Heights, Denver, Adams County | safety and multimodal improvements to create a community serving boulevard.
16 | Northwest Rail | Extend Northwest Rail ( B Line) | From Westminster Station to Downtown Westminster (88th/Harlan) or next reasonable phase | Westminster | Construct next three miles of B Line and S station at Downtown Westminster, or next reasonable phase, or Peak Hour Start up Service | Transit | under development | Work with RTD to determine feasibility for peak hour service. BNSF has received the request and a subsequent study is needed. RTD needs to fund the BNSF study. Westminster is studying cost of three mile extension. |  |  |  | BNSF requires futher study to be fudned by RTD. | 1 | TIER II | all
Endorsed Projects -- actively pursuing support/monitoring - Inter sub regional/multi-county benefits (Tier II includes studies and projects with smaller areas of influence, and NATA members take lead)
17 | I-76 | New Interchange | I-76 & Bridge St. | Brighton | Add ramps to current overpass | Operational Improvements | 10000000 | Support Brighton's request to include FC- RTP Encourage NEPA to start in Sept. |  |  | Include in 2035 FC-RTP for $20 million
| I-25 | Interregional Connectivity Study (ICS) | High Speed Rail north to Fort Collins and south to Colorado Springs. | TBD (final alignment still not finalized) |  | Transit | [5 empty] | CDOT updated the ICS study in 2017 to include two additional alternates - all three alternatives use the station at 162nd and Colorado (end of "N" Line).
18 | North Metro Commuter Rail Extension to Longmont | Commuter Rail | Between RTD "N" Line and Longmont | TBD (final alignment still not finalized) | Commuter Rail between RTD and Longmont including station(s) for Tri-towns. | Transit | [5 empty] | CDOT has completed a commuter rail study and proposed it's inclusion on the 10-year plan.
25 | North Metro Rail | North Metro (N Line) First / Last Mile Connections | At stations, 72nd Avenue to 124th Avenue | Thornton, Eastlake | Provide first / last mile connections to stations | Transit, bicycle, and Pedestrian |  | Look at alternative transit services. | RTD, DRCOG | Developer, DRCOG, RTD, local |  | Trails, sidewalks and bicycle lanes being complete. RTD is bus routing changes go to Board in 2020, RTD starting to install bus stop improvements. | 2
19 | US 287 | Arterial BRT Improvements | Longmont to Broomfield P&R to downtown Denver | Longmont, Lafayette, Broomfield | Main Street & CO 66 to Broomfield P-n-R @ Uptown Ave/Wadsworth (local jurisdictions desire service to continue down US 36 into Downtown Denver) | Transit | 39758740 | Support in NAMS study recommendation Work with RTD and other jurisdictions to identify funding. Begin Multimodal Study, led by Boulder County | RTD RAM | RAMP FASTER Transit SmallStarts NewStarts (corridor-based) RTD DRCOG |  | Pending NAMS TAC meeting scheduled for Provide letter of support that Sharon Richardson can present at the April 18th PAC meeting in support of Arterial BRT along this corridor.
21 | US 85 | PEL: Transit Operational Improvements | Pavilions, south of CO 7 on NB side | ??? | Add NB bus slip ramp for RTD bus operations | Operational Improvements | TBD | Visit configuration of slip ramps in PEL study
22 | 120th Avenue | Key intersection improvements for safety and transit enhancement. | Zuni and Pecos | ??? | Evaluate dedicated right turn lanes and que jumps for transit. | Operational and Transit |  |  |  | STP Metro, Local |  |  | 2 | TIER II |  | group w/ 120th corridor
24 |  | Widening US-85 to E-470 | Initial project would widen from Chambers Road to E-470 (1.35 miles) | Brighton, Commerce City, Adams County | The project will widen 1.35 miles of roadway from 2 lanes (one in each direction) to 4 lanes (two in each direction) with on-street bike lanes and an adjacent sidewalk & multi-use trail. Interconnection of the traffic signals will occur in order to improve corridor efficiency and levels of service. New signals will be installed, as warranted. | Capacity, traffic operations, bicycle and pedestrian improvements | $15.5M | Determine project scope; identify partnerships & funding from local developers |  | DRCOG Developer |  |  | 2 |  |  | 120th corridor
26 | Bike Share | Bike share in multiple jurisdictions, sub-regional impact | At stations, 72nd Avenue to 124th Avenue | Thornton, Eastlake | Implementation of Bike Share program | Bicycle |  | Work with Smart Commute on possible master contract. Continue to explore if feasible. Develop agreement to have Smart Commute run the program. | Private | Private |  | Exploring possible locations | 2
27 | 72nd Avenue | Conduct a study to determine safety and mobility improvements for 72nd Avenue | 72nd Ave between Sheridan and Lowell Blvds. | Westminster | Study to assess the repurposing of 72nd Avenue to included widening the sidewalks, enhancing transit stops and bicycle facility connections. | Pedestrian and transit | $150K |  |  | DRCOG STAMP Grant |  | Concept Study | 3 | Tier III
28 | Federal Boulevard | Conduct a study to determine needs for multi-modal infrastructure. | Denver County Line to W. 92nd Avenue | Federal Heights, Westminster, Denver | Study to establish a transportation vision for Federal Boulevard that addresses pedestrian safety issues and recommends multi-modal transportation infrastructure. | Transit and pedestrian | $200K |  |  | DRCOG STAMP Grant |  | Concept Study | 3 | Tier III
29 | 88th Avenue | Widening from 2 lanes to 4 lanes with bike lanes, trails & sidewalks | I-76 to Highway 2 | Commerce City | 88th Avenue is a regional roadway serving as a connection between a freeway and a major regional arterial. The project will widen 1.6 miles of roadway from 2 lanes (one in each direction) to 4 lanes (two in each direction) and on-street bike lanes with an adjacent sidewalk & multi-use trail. Interconnection of the traffic signals will occur in order to improve corridor efficiency and levels of service. | capacity, traffic operations, pedestrian & bicycle | $26.2M | A design firm will be selected in late-2017/early-2018 to complete the preliminary design and NEPA clearance. Goal is to complete this work by the end of 2018. | $300K included in DRCOG RTP for NEPA and preliminary design Final Design/ROW Preconstruction Activities/ROW FY2020 - $1.5M (DRCOG) FY2021 - $.5M (DRCOG) Local Funds - $2M | DRCOG BUILD GRANT | NEPA & Preliminary design included in 2035 FC-RTP | Consultant selection process is underway. | 3
30 | West 144th Avenue/ Dillon Road (Remove from List? Construction to be complete in 2020, locally funded by Broomfield) | Dillon Rd/ West 144th Ave Improvements | Northwest Parkway to Zuni | Broomfield | Dillon Rd/W 144th is a regional roadway with connectivity to US 287 and I-25. The project will widen the 4-mile Dillon Road/West 144th Avenue corridor through Broomfield to four continuous through lanes from US 287 to Zuni Street. The roadway will be designed in general conformance with the master plan and will include pedestrian/bicycle access improvements. | capacity, traffic operations, pedestrian & bicycle | $40.2 M |  |  |  | YES - local project |  | 2
31 | 160th Avenue | 160th Avenue Improvements | Sheridan to I-25 | Broomfield | Add lanes 3 & 4 | Capacity, traffic operations, pedestrian/ bicycle | $3.8 M |  |  |  | YES - local project |  | 2
32 | CO 7 Is this now part of earlier SH 7? | Implementation of PEL's | Brighton to US 287 (NEW) | ??? | Widen Road, install bike lanes, trails, sidewalks, implement BRT, implement PEL | Capacity, Transit, Bicycle and Pedestrian |  | Continue to have work done with development. Work with CDOT to put on 10-year plan. |  | FASTER Transit, SB17-267, Developer, STP |  | Portions are being widened by development. Other areas will require government funding. | 2
33 |  | CO 7 Improvements | Boulder County Line to Sheridan Parkway | Lafayette, Erie, Boulder | widen from 2 to 4 lanes, multimodal improvements | capacity, operations, multimodal, bus rapid transit | $6.6M |  |  |  | YES - local project |  | 2
34 |  | CO 7 Improvements | Sheridan Parkway to I-25 | Broomfield | Widen from 2 to 4 lanes, multimodal improvements | capacity, operations, multimodal, bus rapid transit | $10.2 M |  |  |  | YES - local project |  | 2
35 |  | CO7 at Huron Grade separated crossing | CO7 at Huron | Broomfield | Pedestrian and bicycle grade separated crossing. Crossing is on a major regional trail. The Broomfield Trail provides a connection from the Great Western Reservoir Open Space in southwest Broomfield to the northeast, east of I-25. The trail crosses the US 287 and CO 7 corridors as well. Upon completion will be 22.5 mile trail. | pedestrian, bicycle, multi-modal, support BRT | [6 empty] | 2
36 | Northwest Parkway | Northwest Parkway Trail Underpass Retrofit | Northwest Parkway Trail west of Wildgrass | Louisville, Broomfield | Retrofit a substandard underpass. Project will connect from trails in Wildgrass to Rock Creek Trail and Coal Creek Trail, upon completion of the trail Broomfield and Louisville and the I-25 corridor will be connected. | pedestrian, bicycle, supports multimodal | Vision Project | [5 empty] | 3 |  |  | Is this a DRCOG project b//c it's going to be interconnected?
37-awaiting approval since outside of NATA boundaries | US 287 (Remove from list? Compete in 2020) | US 287 to US 36, Hoyt Street Pedestrian & Bicycle Overpass | Midway Blvd to Industrial Lane | Broomfield | Build an overpass over BNSF railroad and Industrial Lane at Hoyt Street. Grade separated crossing connects the underpass to US 36 Bikeway. Project is critical to connecting US 287 via Midway Blvd to US 36 Bikeway | pedestrian & bicycle, supports multimodal | $3.1M | [5 empty] | 2 |  |  | wait for determination if this gets removed from list because it goes west of 287 (outside of NATA boundaries; DRCOG project) and doesn't meet all criteria
| McKay Road Imprvements | McKay Road Improvements | between 112th Avenue and 96th Avenue | Thornton, Commerce City | Widen to 4 through lanes with bike lanes, multimodal improvements, new bridge over the South Platte River includes several new traffic signals, storm drainage and water quality improvements | Capacity, traffic operations, pedestrian, bicycle |  | Need to add McKay Road as a principal arterial in the 2050 MVRTP
Horizon Projects
38 | CO 119 | Queue Jumps/AUX lanes or additional travel lane in each direction | Sunset St to Bowen St | Longmont | Add additional capacity and either auxiliary lanes with queue jumps for buses or vehicular through lanes | Capacity, transit, bicycle and pedestrian
39 | Sheridan Blvd. | CO 95 Capacity Improvements | 88th Avenue to 91st Avenue | Westminster | Roadway widening and replacement of bridge over BNSF to accommodate B Line Extension | Capacity, transit |  | 2017 TIGER Grant submission requested widening from US 36 Bridge to 88th Ave. |  | TBD |  |  | 4
40 | Thornton Parkway | Thornton Parkway / 96th Avenue over the South Platte River | Between I-76 and Riverdale Road | Thornton | Widening and Extension of Thornton Parkway over the South Platte River | Capacity, Transit, Bicycle and Pedestrian |  | Adopt an IGA to preserve ROW, Start PEL process, update DRCOG FC-RTP as appropriate |  | Developer |  | Adams County/Thornton IGA preserves part of the ROW | 4 |  |  | Should this be included in the Sheridan project?
41 | Undefined areas | Provide bus service in transit drought islands and areas | Areas not currently served | TBD | Transit service study of bus service to major employment and residential areas that meet RTD service area guidelines | Transit |  | Work with RTD to have service. |  |  |  | Wagon Road/144th Avenue FlexRide Pilot underway for area bounded by Huron St., 144th Avenue, Washington St., and 136th Avenue | 4
42 | State highways (i.e. CO 7, US 287, 120th) | Regional signal optimization and safety project |  | TBD |  | Operations |  | Work with DRCOG. | [7 empty] | Follow-up
43 | West 144th Avenue/ Dillon Road | Sheridan & 144th Ped/Bike Crossing | Sheridan Blvd at W 144th | Broomfield | Pedestrian and bicycle grade separated crossing. Crossing is on a major regional trail. The Broomfield Trail provides a connection from southwest Broomfield to the northeast, east of I-25. The trail crosses the US 287 and CO 7 corridors as well. Upon completion will be 22.5 mile trail. | pedestrian & bicycle, supports multimodal | Vision Project | [5 empty] | 4 |  |  | first needs study
44 | 160th Avenue | 160th Avenue Overpass | 160th Ave at I-25 | Broomfield, Thornton | Expand capacity at 160th overpass | Capacity, traffic operations, pedestrian/ bicycle | Vision Project | [5 empty] | not discussed in meeting
45 | Sheridan Parkway | Sheridan - Lowell to NW Parkway | Lowell to NW Parkway | Broomfield | Developers will widen road to 4 lanes, ultimate requires a 6 lane expansion. | capacity, operational improvements, ped/bicycle improvements | $7.6 M |  |  |  | YES - local project |  | 4
46 |  | Sheridan - NW Parkway to CO 7 | NW Parkway to CO 7 | Broomfield | Add lanes 3 & 4 | capacity, operational improvements, ped/bicycle improvements | $5.7 M |  |  |  | YES - local project |  | 4 |  |  | potentially combined with Sheridan & I-25 interchange project?
47 |  | Sheridan - CO 7 to Weld County Road 11 | CO7 to Weld County Road 11 | Erie | Expand and extend Sheridan Road from CO 7 to Weld County Road 11, crossing I-25 | capacity, operational improvements, ped/bicycle improvements | Vision Project | [5 empty] | 4
48 | I-25 | Sheridan & I-25 interchange | Sheridan Parkway at I-25 | ??? | New interstate interchange at the new Sheridan road expansion, project will include grade separated pedestrian and bicycle facilities | capacity, operational improvements, ped/bicycle improvements | Vision Project | [5 empty] | 4 |  |  | potentially combined with Sheridan Blvd., SH7 to I-25 project
49 |  | Regional pedestrian and bike path similar to US 36 |  | TBD | [8 empty] | 4 |  |  | Bundle under I-25 corridor. First needs feasibility study and more clarification
50 |  | Broomfield Trail & Bull Canal Grade Separated Crossing | Broomfield Trail at I-25 | Broomfield | Pedestrian and bicycle grade separated crossing on Broomfield Trail & Bull Canal at I-25. Crossing is on a major regional trail. The Broomfield Trail provides a connection from southwest Broomfield to the northeast, east of I-25. The trail crosses the US 287 and CO 7 corridors as well. Upon completion will be 22.5 mile trail. | pedestrian, bicycle, multi-modal | [6 empty] | 4
51 | Huron Street | Huron Street Improvements | 150th Avenue to 160th Avenue | Broomfield | Add lanes 3 & 4 | Capacity, traffic operations, pedestrian/ bicycle, multimodal potential BRT connection at CO7 micro mobility hub | $8.6 M |  |  |  | YES - local project |  | not discussed in meeting
|  | Colorado Boulevard | 152nd Avenue to 168th Avenue | Adams County | Relocate and Realign, widen, multimodal improvements including pedestrian, bicycle and accommodate future bus | Capacity, traffic operations, pedestrian/ bicycle, multimodal potential BRT connection at CO7 micro mobility hub
52 |  | Huron Street Improvements | 160th Avenue to CO 7 | Broomfield | Relocate and add lanes 3 &4 | Capacity, traffic operations, pedestrian/ bicycle, multimodal potential BRT connection at CO7 micro mobility hub | $5.1 M |  |  |  | YES - local project |  | not discussed in meeting